## How to use
Free Job Costing Spreadsheet: how to use it
Start here:
Yellow cells are yours to fill in. Green-grey cells hold formulas: leave them alone and they fill themselves.
The example file is filled with fictional data so you can see every number working. The blank file is the same workbook, empty: use that one.
Google Sheets: File > Import > Upload the .xlsx (or open it from Google Drive), then File > Save as Google Sheets. Excel: just open it (Excel 2010 or newer). Numbers on Mac also opens it.
Set up (5 minutes):
1. Settings: your cost categories (up to 8) and the year (B11).
2. Jobs: one row per job (up to 20): the contract value you agreed and your budget (estimated cost).
3. Costs: every receipt and timesheet: date, job, category, amount. Costs to date, budget left and an OVER BUDGET flag update on the Jobs tab.
What you get:
Jobs: costs to date, budget left, OVER BUDGET flags, margin at budget and budget used per job. Dashboard: totals for all jobs and costs by category.
Limits: 20 jobs and 300 cost rows. This is a record-keeping tool, not an invoice generator or tax advice. Need invoices, billed vs collected, job status and a month-by-month cash table? See the paid Contractor Job Cost tracker at tuper.app/templates.
Help:
Something wrong? Message us at support@tuper.app and we fix it.
Designed by Tuper. Built with AI tools and tested by us; tell us if anything breaks.

## Dashboard
All jobs | Total | Cost category | Year total
Contract value
Budget
Costs to date
Contract value minus costs
Jobs over budget

## Settings
Cost category
Labour
Materials
Subcontractor
Equipment rental
Permits and fees
Disposal
Fuel and travel
Other
Year | 2026

## Jobs
Job | Client | Contract value | Budget (est. cost) | Costs to date | Budget left | Budget flag | Margin at budget | Budget used
Kitchen remodel, Oak St | R. Alvarez | 28500 | 21000
Deck rebuild, Elm Ave | P. Nguyen | 9800 | 7100
Bathroom retile | S. Brooks | 6400 | 4300
Garage conversion | M. Dietrich | 18200 | 13500
Fence and gate | L. Haddad | 5200 | 3300

## Costs
Date | Job | Category | Vendor / note | Amount | Year
2026-02-11 | Fence and gate | Labour | Crew timesheet | 1300
2026-02-19 | Deck rebuild, Elm Ave | Equipment rental | Supplier invoice | 380
2026-03-08 | Kitchen remodel, Oak St | Labour | Crew timesheet | 4200
2026-03-16 | Fence and gate | Equipment rental | Supplier invoice | 220
2026-03-24 | Deck rebuild, Elm Ave | Permits and fees | Supplier invoice | 250
2026-04-05 | Bathroom retile | Labour | Crew timesheet | 1800
2026-04-13 | Kitchen remodel, Oak St | Materials | Supplier invoice | 5600
2026-05-10 | Bathroom retile | Materials | Supplier invoice | 1450
2026-05-18 | Kitchen remodel, Oak St | Subcontractor | Supplier invoice | 3100
2026-06-15 | Bathroom retile | Disposal | Supplier invoice | 180
2026-06-23 | Kitchen remodel, Oak St | Materials | Supplier invoice | 2900
2026-07-04 | Deck rebuild, Elm Ave | Labour | Crew timesheet | 2600
2026-07-20 | Garage conversion | Permits and fees | Supplier invoice | 640
2026-08-09 | Deck rebuild, Elm Ave | Materials | Supplier invoice | 3200
2026-08-25 | Garage conversion | Labour | Crew timesheet | 1900
2026-09-06 | Fence and gate | Materials | Supplier invoice | 1850
2026-09-14 | Deck rebuild, Elm Ave | Disposal | Supplier invoice | 420
2026-10-22 | Deck rebuild, Elm Ave | Materials | Extra hardware and fixings | 1500